## Functional
Annexure - 16
RSETI - STATUS OF LAND ALLOTMENT IN THE STATE OF PUNJAB AS ON 30.09.2024
Part A (Functioning without any issue) -15
Sr.No. | District | From where functioning | Sr.No. | District | From where functioning | Sr.No. | District | From where functioning
1 | AMRITSAR Lead Bank- PNB | OWN BUILDING | 6 | FEROZEPUR Lead Bank- PNB | OWN BULDING | 11 | SRI MUKTSAR SAHIB Lead Bank- SBI | OWN BUILDING
2 | BARNALA Lead Bank- SBI | OWN BUILDING | 7 | KAPURTHALA Lead Bank- PNB | OWN BUILDING | 12 | PATIALA Lead Bank- SBI | (RENTAL) VILLAGE-JASSOWAL,BHADSON ROAD,PATIALA
3 | BATHINDA Lead Bank- SBI | (RENTAL) RED CROSS BHAWAN, BATHINDA | 8 | LUDHIANA Lead Bank- PSB | OWN BUILDING | 13 | ROPAR Lead Bank- UCO | OWN BUILDING
4 | FARIDKOT Lead Bank- PSB | OWN BUILDING | 9 | MANSA Lead Bank- SBI | OWN BUILDING | 14 | SANGRUR Lead Bank- SBI | OWN BUILDING
5 | FATEHGARH SAHIB Lead Bank- SBI | (RENTAL) OPP. BSNL EXCHANGE, INSIDE BDPO OFFICE SIRHIND, FATEHGARH SAHIB | 10 | MOGA Lead Bank- PSB | OWN BUILDING | 15 | GURDASPUR Lead Bank- PNB | (RENTAL) OPPOSITE HAPPY SCHOOL , BABOWAL ROAD GURDASPUR.
Part B (Functioning and having issues) - 3
Sr.No. | District | From where functioning | Whether land has been allocated | Whether possession of land has taken (if not, reasons thereof) | Whether Building Plan has been got approved from the competent authority | Whether construction has started | Tentative Date for completion of construction, if commenced. | Amount of Charges paid for CLU, EDC etc.
1 | JALANDHAR Lead Bank- UCO | PLOT NO. 7/235 NEW VIJAY NAGAR JALANDHAR | NO | The project architect Ghai has prepared the new plan/sketch of the new RUDSETI Building to be constructed at Basti Danishmandan, Jalandhar. We have got approval for the same from our honourable President. Soil testing has been done on this land. Structure Designing and 3D renders of the proposed RUDSET Institute Jalandhar have been sent for approval. we have submitted the site plan (File No: PB/JUC/JALAN/162360 DATED 13.02.2023) to the Municipal Corporation Jalandhar for their approval and the requisite fees already deposited for the same. Some objections/queries have been raised by the Municipal Corporation Jalandhar. One of them is to provide a detailed Chajra plan. For which we had a discussion with patwari and trying to obtain as per the queries raised. We also visited Municipal Corporation, Jalandhar and met with ATP and MTP and discussed about the queries raised includes details of the leftover space, chajra plan, plot demarcation etc. Now we are further looking up the matter so that we could get approval of the site plan at earliest.
2 | HOSHIARPUR Lead Bank- PNB | RENTED BUILDING. PROVIDED BY DISTT. ADMINISTRATION (ZILLA PARISHAD), HOSHIARPUR WHICH TOO IS INADEQUATE. PAYING RENT OF RS.8000/- PER MONTH | NO | Village Panchyat demanded Rs. 1 Lakh per year as rent with yearly increase 2%. Head Office of PNB has asked allotment of land for free of cost/rent as per Ministery of Rural Development (MoRD) guidelines. In view of this case for allotment of land free of cost/rent at another place again taken up with District Administration on 30.07.2024.
3 | SAS NAGAR Lead Bank- PNB | PLOT NO.1, VIKAS BHAWAN, SECTOR 62,MOHALI | NO | All the queries raised by the dealing patwari have been replied and DDPO Mohali has again requested Head Quarter of Rural Development to allot the land to Rseti with 10% increase in annual lease rent.

## Non Functional
Annexure- 16 contd.
Sr.No. | District | Issues
1 | PATHANKOT Lead Bank- PNB | The Trust board has deferred the agenda and directed to review the proposal for opening of 3 new RSETIs in Punjab State (TaranTaran, Pathankot and SBS Nagar) and advised Zonal Office, Amritsar to explore the possibility to arrange the training of candidate of these districts to nearby RSETIs.”
2 | TARN TARAN Lead Bank- PNB | The Trust board has deferred the agenda and directed to review the proposal for opening of 3 new RSETIs in Punjab State (TaranTaran, Pathankot and SBS Nagar) and advised Zonal Office, Amritsar to explore the possibility to arrange the training of candidate of these districts to nearby RSETIs.”
3 | FAZILKA Lead Bank- PNB | The Trust board has deferred the agenda and directed to review the proposal for opening of new RSETIs at Fazilka district of Punjab State and advised Zonal Office, Ludhiana to explore the possibility to arrange the training of candidates of Fazilka district to nearby RSETIs.
4 | SBS NAGAR Lead Bank- PNB | The Trust board has deferred the agenda and directed to review the proposal for opening of new RSETIs at Fazilka district of Punjab State and advised Zonal Office, Ludhiana to explore the possibility to arrange the training of candidates of Fazilka district to nearby RSETIs.
5 | MALERKOTLA | MORD has not approved RSETI at Malerkotla, looking into the potential.